{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet2","index":0,"n_rows":23,"n_cols":7,"rows_kept":23,"cut":false,"hidden":false,"merged":[[9,1,9,6],[6,0,6,6],[7,0,7,6],[5,0,5,6]],"flags":["formulas_cached_only"]}
[{"$nulls":5},"Attachment A"]
[]
[]
[]
[]
["Communications & Liaison"]
["Nationwide Tax Forums"]
["2009  Customer Surveys Schedule"]
[]
["ACTIVITIES","DATES:"]
[null,"Las Vegas, NV","San Diego, CA","Orlando, FL","New YorK, NY","Dallas, TX","Atlanta, GA"]
["Tax Forums --> ","July 7-8","July 14-16","Aug 4-6","Aug 25-27","Sept 8-10","Sept 22-24"]
["Prepare List of Attendees"]
["Forward to Vendor","2009-07-20","2009-07-28","2009-08-18","2009-09-09","2009-09-22","2009-10-06"]
["Program list","2009-07-21","2009-07-29","2009-08-19","2009-09-10","2009-09-23","2009-10-07"]
["Administer Survey & Collect/Maintain Results"]
["Send E-mail to respondents","2009-07-22","2009-07-30","2009-08-20","2009-09-11","2009-09-24","2009-10-08"]
["End of data collection","2009-08-11","2009-08-19","2009-09-10","2009-10-02","2009-10-15","2009-10-29"]
["Analyze & Report Results"]
["Prepare Draft Report","2009-11-27"]
["Review "]
["Consolidate comments & Forward to Vendor","2009-12-07"]
["Prepare Final Report","2009-12-11"]