{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet2","index":0,"n_rows":19,"n_cols":7,"rows_kept":19,"cut":false,"hidden":false,"merged":[[0,0,0,6],[1,0,1,6],[2,0,2,6]],"flags":["formulas_cached_only"]}
["Communications & Liaison"]
["Nationwide Tax Forums"]
["2010  Customer Satisfaction Survey Schedule"]
[]
[]
[null,null,null,"DATES & LOCATIONS OF TAX FORUMS:"]
["ACTIVITIES","Atlanta, GA","Chicago, IL","Orlando, FL","New YorK, NY","Las Vegas, NV","San Diego, CA"]
[null,"June 21-24","July 12-15","July 26-29","Aug 9-12","Aug 23-26","Aug 30 - Sep 2"]
["Prepare List of Attendees"]
["Forward to Vendor","2010-07-09","2010-07-30","2010-08-13","2010-08-27","2010-09-10","2010-09-17"]
["Program list","2010-07-13","2010-08-03","2010-08-17","2010-08-31","2010-09-14","2010-09-21"]
["Administer Survey & Collect/Maintain Results"]
["Send Survey via E-mail to respondents","2010-07-19","2010-08-09","2010-08-23","2010-09-07","2010-09-20","2010-09-27"]
["End of data collection","2010-08-09","2010-09-02","2010-09-13","2010-09-28","2010-10-11","2010-10-18"]
["Analyze & Report Results"]
["Prepare Draft Report",{"$nulls":5},"2010-11-17"]
["Review ",{"$nulls":5},"2010-11-29"]
["Consolidate comments & Forward to Vendor",{"$nulls":5},"2010-12-06"]
["Prepare Final Report",{"$nulls":5},"2010-12-13"]