{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet2","index":0,"n_rows":23,"n_cols":7,"rows_kept":23,"cut":false,"hidden":false,"merged":[[9,1,9,6],[6,0,6,6],[7,0,7,6]],"flags":["formulas_cached_only"]}
[{"$nulls":5},"Attachment A"]
[]
[]
[]
[]
[]
["National Public Liaison - Nationwide Tax Forums"]
["Customer Surveys Schedule"]
[]
["ACTIVITIES","DATES:"]
[null,"Atlanta, GA","Chicago, IL","Orlando, FL","Las Vegas, NV","NY, NY","San Diego, CA"]
["Tax Forums --> ","July 1-3","July 22-24","Aug 5-7","Aug. 19-21","Aug. 26-28","Sept 9-11"]
["Prepare List of Attendees"]
["Forward to Vendor","2008-07-16","2008-08-05","2008-08-19","2008-09-03","2008-09-09","2008-09-23"]
["Program list","2008-07-17","2008-08-06","2008-08-20","2008-09-04","2008-09-10","2008-09-24"]
["Administer Survey & Collect/Maintain Results"]
["Send E-mail to respondents","2008-07-18","2008-08-07","2008-08-21","2008-09-05","2008-09-11","2008-09-25"]
["End of data collection","2008-08-07","2008-08-27","2008-09-11","2008-09-25","2008-10-01","2008-10-15"]
["Analyze & Report Results"]
["Prepare Draft Report","2008-11-12"]
["Review "]
["Consolidate comments & Forward to Vendor","11/212008"]
["Prepare Final Report","2008-11-25"]